## Hours
|  |  | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 2023-08-06 | 2023-08-13 | 2023-08-20 | 2023-08-27 | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19
|  | Person Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1. | Choose Location | Erica | 2023-02-12: 6; 2023-02-19: 6; 2023-02-26: 6; 2023-03-05: 6; 2023-03-12: 6 | 30 | *Note that the time Safety Margin has already been added to the Critical Path here
2. | Get Permit | Ann | 2023-03-19: 4; 2023-03-26: O; 2023-04-02: O; 2023-04-09: O; 2023-04-16: O; 2023-04-23: O; 2023-04-30: O; 2023-05-07: O; 2023-05-14: O; 2023-05-21: O; 2023-05-28: O; 2023-06-04: O; 2023-06-11: 4 | 8
3. | Purchase Site | Sara | 2023-06-18: 5; 2023-06-25: O; 2023-07-02: O; 2023-07-09: O; 2023-07-16: O; 2023-07-23: 6; 2023-07-30: O; 2023-08-06: O; 2023-08-13: O; 2023-08-20: O; 2023-08-27: O; 2023-09-03: 4 | 15
4. | Modify Building | Amber | 2023-08-27: 12; 2023-09-03: 12; 2023-09-10: 12; 2023-09-17: 15; 2023-09-24: 15; 2023-10-01: 15; 2023-10-08: 18; 2023-10-15: 18; 2023-10-22: 18; 2023-10-29: 18 | 153
5. | Install Furniture | Justice | 2023-11-05: 7; 2023-11-12: 7; 2023-11-19: 8 | 22
6. | Open
7. | Find Site | Juliana | 2023-04-02: 6; 2023-04-09: 6; 2023-04-16: 12; 2023-04-23: 12; 2023-04-30: 6 | 42
8. | Hire Manager | Joshua | 2023-03-26: 4; 2023-04-02: 12; 2023-04-09: 12; 2023-04-16: 12; 2023-04-23: 4; 2023-04-30: 4 | 48
9. | Buy furniture | Lindy | 2023-10-01: 8; 2023-10-08: 2 | 10
10. | Hire Staff | Julian | 2023-10-01: 4; 2023-10-08: 12; 2023-10-15: 12; 2023-10-22: 12; 2023-10-29: 4; 2023-11-05: 4; 2023-11-12: 2; 2023-11-19: 2 | 52
|  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 18 | 18 | 24 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | 16 | 12 | 15 | 15 | 27 | 32 | 30 | 30 | 22 | 11 | 9 | 10 | 380
4 Reasons Gantt Charts are Very Helpful in the Project Management Process
1. Communication: Gantt charts show others what is involved in completeing a given project.
2. Resource Planning: A Gantt chart allows one to easily see how busy one will be in any given week (and it also shows when resource constraints might bottle neck); simply look vertically and
take note of where constraints might be, with special attention given to which week/time period will be most affected.
3. Monitoring Progress: One can easily monitor time and budget progress by coloring in results as one sweeps from left to right across the Gantt chart (in contrast, crossing tasks off a list can
indeed tell a person what has been completed, but it cannot show what has been done compared to what should have done at any given time.)
4. Interpreting Costs: One can make sense of what has been spent; if half of the budget has been spent, it should be noticeable whether or not half of the work has been completed (or
one should be able to tell why less than half of the budget has been spent even though the project has passed the half-way time mark, which can happen, for instance, if an especially expensive task
is coming up.) Or maybe the project is only 1/4 way along in terms of time duration, but 1/2 of the budget has already been spent - the project accountant may not detect the problem this since,
technically, there has not yet been overspend, but by way of this Gantt chart, it is clear spending is not going according to schedule. With these charts, potentinal problems like this can
more easily be monitored.
S = 8
S = 22
S = 22
S = 25

## Costs - 1
|  |  | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 2023-08-06 | 2023-08-13 | 2023-08-20 | 2023-08-27 | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19
|  | Person Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1. | Choose Location | Erica | 2023-02-12: 2; 2023-02-19: 2; 2023-02-26: 2; 2023-03-05: 2; 2023-03-12: 2 | 10
2. | Get Permit | Ann | 2023-03-19: 99; 2023-03-26: O; 2023-04-02: O; 2023-04-09: O; 2023-04-16: O; 2023-04-23: O; 2023-04-30: O; 2023-05-07: O; 2023-05-14: O; 2023-05-21: O; 2023-05-28: O; 2023-06-04: O; 2023-06-11: 80 | 179
3. | Purchase Site | Sara | 2023-06-18: 120; 2023-06-25: O; 2023-07-02: O; 2023-07-09: O; 2023-07-16: O; 2023-07-23: 150; 2023-07-30: O; 2023-08-06: O; 2023-08-13: O; 2023-08-20: O; 2023-08-27: O; 2023-09-03: 130 | 400
4. | Modify Building | Amber | 2023-08-27: 22; 2023-09-03: 25; 2023-09-10: 224; 2023-09-17: 22; 2023-09-24: 12; 2023-10-01: 12; 2023-10-08: 12; 2023-10-15: 16; 2023-10-22: 26; 2023-10-29: 33 | 404
5. | Install Furniture | Justice | 2023-11-05: 8; 2023-11-12: 7; 2023-11-19: 9 | 24
6. | Open
7. | Find Site | Juliana | 2023-04-02: 12; 2023-04-09: 12; 2023-04-16: 15; 2023-04-23: 15; 2023-04-30: 18 | 72
8. | Hire Manager | Joshua | 2023-03-26: 5; 2023-04-02: 5; 2023-04-09: 5; 2023-04-16: 8; 2023-04-23: 8; 2023-04-30: 8 | 39
9. | Buy furniture | Lindy | 2023-10-01: 87; 2023-10-08: 44 | 131
10. | Hire Staff | Julian | 2023-10-01: 5; 2023-10-08: 5; 2023-10-15: 5; 2023-10-22: 8; 2023-10-29: 8; 2023-11-05: 8; 2023-11-12: O; 2023-11-19: O | 39
|  |  | 2 | 2 | 2 | 2 | 2 | 99 | 5 | 17 | 17 | 23 | 23 | 26 | 0 | 0 | 0 | 0 | 0 | 80 | 120 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 22 | 155 | 224 | 22 | 12 | 104 | 61 | 21 | 34 | 41 | 16 | 7 | 9 | 1298

## Costs - 2
|  |  | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 2023-08-06 | 2023-08-13 | 2023-08-20 | 2023-08-27 | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19
|  | Person Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1. | Choose Location | Erica | 2023-02-12: 2; 2023-02-19: 2; 2023-02-26: 2; 2023-03-05: 2; 2023-03-12: 2 | 10
2. | Get Permit | Ann | 2023-03-19: 99; 2023-03-26: O; 2023-04-02: O; 2023-04-09: O; 2023-04-16: O; 2023-04-23: O; 2023-04-30: O; 2023-05-07: O; 2023-05-14: O; 2023-05-21: O; 2023-05-28: O; 2023-06-04: O; 2023-06-11: 80 | 179
3. | Purchase Site | Sara | 2023-06-18: 120; 2023-06-25: O; 2023-07-02: O; 2023-07-09: O; 2023-07-16: O; 2023-07-23: 150; 2023-07-30: O; 2023-08-06: O; 2023-08-13: O; 2023-08-20: O; 2023-08-27: O; 2023-09-03: 130 | 400
4. | Modify Building | Amber | 2023-08-27: 22; 2023-09-03: 25; 2023-09-10: 224; 2023-09-17: 22; 2023-09-24: 12; 2023-10-01: 12; 2023-10-08: 12; 2023-10-15: 16; 2023-10-22: 26; 2023-10-29: 33 | 404
5. | Install Furniture | Justice | 2023-11-05: 8; 2023-11-12: 7; 2023-11-19: 9 | 24
6. | Open
7. | Find Site | Juliana | 2023-04-02: 12; 2023-04-09: 12; 2023-04-16: 15; 2023-04-23: 15; 2023-04-30: 18 | 72
8. | Hire Manager | Joshua | 2023-03-26: 5; 2023-04-02: 5; 2023-04-09: 5; 2023-04-16: 8; 2023-04-23: 8; 2023-04-30: 8 | 39
9. | Buy furniture | Lindy | 2023-10-01: 87; 2023-10-08: 44 | 131
10. | Hire Staff | Julian | 2023-10-01: 5; 2023-10-08: 5; 2023-10-15: 5; 2023-10-22: 8; 2023-10-29: 8; 2023-11-05: 8; 2023-11-12: O; 2023-11-19: O | 39
|  |  | 2 | 2 | 2 | 2 | 2 | 99 | 5 | 17 | 17 | 23 | 23 | 26 | 0 | 0 | 0 | 0 | 0 | 80 | 120 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 22 | 155 | 224 | 22 | 12 | 104 | 61 | 21 | 34 | 41 | 16 | 7 | 9 | 1298
[6 empty] | Hours |  |  |  | Costs
Building in Contingency/Safety Margin for Funding/Financial Factors
Remember that, using the 90% rule, we built in a safety margin/contingency to our critical path (by estimating the worst case scenario for every task on the critical path,
adding up those additional time units, aggregating the additional time needed for the worst case scenario, and then halving that in order to arrive at a 90% success
target in terms of project duration. We then went back and peppered that time in bits along the critical path.)
Remember that for this type of "Costs Gantt Chart", there is no critical path, since every step is critical in terms of needing funds to provision the project. Therefore, for
this chart we will need to build in financial contingency for every step represented (not just for those on the critical path.) Thus, using the totals down the right
side of this chart (the totals for both the red Critical Path steps as well as the green, non-Critical Path steps), estimate a worst case scenario for each of these steps,
halve each value so as to arrive at a new 90% contingency value/amount for each step, and then pepper/distribute reasonable portions of that new amount
into each respective step, arriving at new values that, collectively, reflect an aggregate 90% contingency financial buffer for the entire project (your total figure –
in this case, 1,298 or $1,298,000 found at the lower, right-hand corner – will change to reflect a new 90% contingency buffer.) Realize that time values for none of
these steps – the length of each bar – will change by way of this process, since there is no need to build in a time buffer for non-Critical steps (and time contingency
has already been inserted along the Critical Path when you modifed the "Hours Gantt Chart".) The only thing that will change are the values within each
block/week – those values must increase in accordance with your 90% contingency buffer.
For an example of the above sheet reworked with funding contingencies inserted for every step, see the following sheet "Costs with Safety Margin".

## Costs with Safety Margin
|  |  | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 2023-08-06 | 2023-08-13 | 2023-08-20 | 2023-08-27 | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19
|  | Person Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1. | Choose Location | Erica | 2023-02-12: 2; 2023-02-19: 3; 2023-02-26: 4; 2023-03-05: 4; 2023-03-12: 2 | 15
2. | Get Permit | Ann | 2023-03-19: 99; 2023-03-26: 18; 2023-04-02: O; 2023-04-09: O; 2023-04-16: O; 2023-04-23: O; 2023-04-30: O; 2023-05-07: O; 2023-05-14: O; 2023-05-21: O; 2023-05-28: O; 2023-06-04: 18; 2023-06-11: 80 | 215
3. | Purchase Site | Sara | 2023-06-18: 140; 2023-06-25: O; 2023-07-02: O; 2023-07-09: O; 2023-07-16: O; 2023-07-23: 200; 2023-07-30: O; 2023-08-06: O; 2023-08-13: O; 2023-08-20: O; 2023-08-27: 80; 2023-09-03: 80 | 500
4. | Modify Building | Amber | 2023-08-27: 48; 2023-09-03: 35; 2023-09-10: 234; 2023-09-17: 50; 2023-09-24: 22; 2023-10-01: 22; 2023-10-08: 22; 2023-10-15: 26; 2023-10-22: 50; 2023-10-29: 43 | 552
5. | Install Furniture | Justice | 2023-11-05: 9; 2023-11-12: 8; 2023-11-19: 10 | 27
6. | Open
7. | Find Site | Juliana | 2023-04-02: 15; 2023-04-09: 14; 2023-04-16: 16; 2023-04-23: 16; 2023-04-30: 18 | 79
8. | Hire Manager | Joshua | 2023-03-26: 6; 2023-04-02: 6; 2023-04-09: 6; 2023-04-16: 9; 2023-04-23: 9; 2023-04-30: 9 | 45
9. | Buy furniture | Lindy | 2023-10-01: 90; 2023-10-08: 48 | 138
10. | Hire Staff | Julian | 2023-10-01: 6; 2023-10-08: 6; 2023-10-15: 6; 2023-10-22: 9; 2023-10-29: 8; 2023-11-05: 8; 2023-11-12: 1; 2023-11-19: 1 | 45
|  |  | 2 | 3 | 4 | 4 | 2 | 99 | 24 | 21 | 20 | 25 | 25 | 27 | 0 | 0 | 0 | 0 | 18 | 80 | 140 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 128 | 115 | 234 | 50 | 22 | 118 | 76 | 32 | 59 | 51 | 17 | 9 | 11 | 1616
Steps for Adding a Safety Margin to a Costs Gantt Chart
1. Determine a Worst Case Value for Each Step: Using the totals down the right side of the chart,
estimate a worst case scenario for each step.
[9 empty] | Old Values |  |  |  | Worst Case Values
[7 empty] | Choose Location |  |  | 10 |  |  |  |  | 20
[7 empty] | Get Permit |  |  | 179 |  |  |  |  | 250
[7 empty] | Purchase Site |  |  | 400 |  |  |  |  | 600
[7 empty] | Modify Building |  |  | 404 |  |  |  |  | 700
[7 empty] | Install Furniture |  |  | 24 |  |  |  |  | 29
[7 empty] | Open |  |  | 0 |  |  |  |  | 0
[7 empty] | Find Site |  |  | 72 |  |  |  |  | 85
[7 empty] | Hire Manager |  |  | 39 |  |  |  |  | 50
[7 empty] | Buy Furniture |  |  | 131 |  |  |  |  | 145
[7 empty] | Hire Staff |  |  | 39 |  |  |  |  | 50
[9 empty] | 1298 |  |  |  |  | 1929
2. Implement the 90% Rule for Each Step: Halve the value of difference between the worst case value and the old value for each step in order to arrive at a 90% contingency value/amount for each step.
[8 empty] | 90% Differential |  |  |  |  | New
[8 empty] | For Each Step |  |  |  |  | 90% Values
[7 empty] | Choose Location |  |  | 5 |  |  |  |  | 15
[7 empty] | Get Permit |  |  | 36 |  |  |  |  | 215
[7 empty] | Purchase Site |  |  | 100 |  |  |  |  | 500
[7 empty] | Modify Building |  |  | 148 |  |  |  |  | 552
[7 empty] | Install Furniture |  |  | 3 |  |  |  |  | 27
[7 empty] | Open |  |  | 0 |  |  |  |  | 0
[7 empty] | Find Site |  |  | 7 |  |  |  |  | 79
[7 empty] | Hire Manager |  |  | 6 |  |  |  |  | 45
[7 empty] | Buy Furniture |  |  | 7 |  |  |  |  | 138
[7 empty] | Hire Staff |  |  | 6 |  |  |  |  | 45
[8 empty] | Total Buffer/Safety Amount Added = | 318 |  |  |  |  | 1616
3. Adjust Each Step by Adding Safety Margins/Contingencies: Pepper/distribute reasonable portions of each 90% amount into the weeks of each respective step.
I have added these values to each of the step/boxes above (that is why total budgetary needs shown at the bottom right – $1,616.000 – now equals the new Total Buffer/Safety amount.)