## Hours (without Network Diagram)
|  |  | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 2023-08-06 | 2023-08-13 | 2023-08-20 | 2023-08-27 | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19
|  | Person Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1. | Choose Location | Erica | 2023-02-12: 6; 2023-02-19: 6; 2023-02-26: 6; 2023-03-05: 6; 2023-03-12: 6 | 30 | *Note that the time Safety Margin has already been added to the Critical Path here
2. | Get Permit | Ann | 2023-03-19: 4; 2023-03-26: O; 2023-04-02: O; 2023-04-09: O; 2023-04-16: O; 2023-04-23: O; 2023-04-30: O; 2023-05-07: O; 2023-05-14: O; 2023-05-21: O; 2023-05-28: O; 2023-06-04: O; 2023-06-11: 4 | 8
3. | Purchase Site | Sara | 2023-06-18: 5; 2023-06-25: O; 2023-07-02: O; 2023-07-09: O; 2023-07-16: O; 2023-07-23: 6; 2023-07-30: O; 2023-08-06: O; 2023-08-13: O; 2023-08-20: O; 2023-08-27: O; 2023-09-03: 4 | 15
4. | Modify Building | Amber | 2023-08-27: 12; 2023-09-03: 12; 2023-09-10: 12; 2023-09-17: 15; 2023-09-24: 15; 2023-10-01: 15; 2023-10-08: 18; 2023-10-15: 18; 2023-10-22: 18; 2023-10-29: 18 | 153
5. | Install Furniture | Justice | 2023-11-05: 7; 2023-11-12: 7; 2023-11-19: 8 | 22
6. | Open
7. | Find Site | Juliana | 2023-04-02: 6; 2023-04-09: 6; 2023-04-16: 12; 2023-04-23: 12; 2023-04-30: 6 | 42
8. | Hire Manager | Joshua | 2023-03-26: 4; 2023-04-02: 12; 2023-04-09: 12; 2023-04-16: 12; 2023-04-23: 4; 2023-04-30: 4 | 48
9. | Buy furniture | Lindy | 2023-10-01: 8; 2023-10-08: 2 | 10
10. | Hire Staff | Julian | 2023-10-01: 4; 2023-10-08: 12; 2023-10-15: 12; 2023-10-22: 12; 2023-10-29: 4; 2023-11-05: 4; 2023-11-12: 2; 2023-11-19: 2 | 52
|  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 18 | 18 | 24 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | 16 | 12 | 15 | 15 | 27 | 32 | 30 | 30 | 22 | 11 | 9 | 10 | 380
S = 8
S = 22
S = 22
S = 25

## Hours (with Network Diagram)
|  |  | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 2023-08-06 | 2023-08-13 | 2023-08-20 | 2023-08-27 | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19
|  | Person Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1. | Choose Location | Erica | 2023-02-12: 6; 2023-02-19: 6; 2023-02-26: 6; 2023-03-05: 6; 2023-03-12: 6 | 30 | *Note that the time Safety Margin has already been added to the Critical Path here
2. | Get Permit | Ann | 2023-03-19: 4; 2023-03-26: O; 2023-04-02: O; 2023-04-09: O; 2023-04-16: O; 2023-04-23: O; 2023-04-30: O; 2023-05-07: O; 2023-05-14: O; 2023-05-21: O; 2023-05-28: O; 2023-06-04: O; 2023-06-11: 4 | 8
3. | Purchase Site | Sara | 2023-06-18: 5; 2023-06-25: O; 2023-07-02: O; 2023-07-09: O; 2023-07-16: O; 2023-07-23: 6; 2023-07-30: O; 2023-08-06: O; 2023-08-13: O; 2023-08-20: O; 2023-08-27: O; 2023-09-03: 4 | 15
4. | Modify Building | Amber | 2023-08-27: 12; 2023-09-03: 12; 2023-09-10: 12; 2023-09-17: 15; 2023-09-24: 15; 2023-10-01: 15; 2023-10-08: 18; 2023-10-15: 18; 2023-10-22: 18; 2023-10-29: 18 | 153
5. | Install Furniture | Justice | 2023-11-05: 7; 2023-11-12: 7; 2023-11-19: 8 | 22
6. | Open
7. | Find Site | Juliana | 2023-04-02: 6; 2023-04-09: 6; 2023-04-16: 12; 2023-04-23: 12; 2023-04-30: 6 | 42
8. | Hire Manager | Joshua | 2023-03-26: 4; 2023-04-02: 12; 2023-04-09: 12; 2023-04-16: 12; 2023-04-23: 4; 2023-04-30: 4 | 48
9. | Buy furniture | Lindy | 2023-10-01: 8; 2023-10-08: 2 | 10
10. | Hire Staff | Julian | 2023-10-01: 4; 2023-10-08: 12; 2023-10-15: 12; 2023-10-22: 12; 2023-10-29: 4; 2023-11-05: 4; 2023-11-12: 2; 2023-11-19: 2 | 52
|  |  | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 18 | 18 | 24 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | 16 | 12 | 15 | 15 | 27 | 32 | 30 | 30 | 22 | 11 | 9 | 10 | 380
4 Reasons Gantt Charts are Very Helpful in the Project Management Process
1. Communication: Gantt charts show others what is involved in completeing a given project.
2. Resource Planning: A Gantt chart allows one to easily see how busy one will be in any given week (and it also shows when resource constraints might bottle neck); simply look vertically and
take note of where constraints might be, with special attention given to which week/time period will be most affected.
3. Monitoring Progress: One can easily monitor time and budget progress by coloring in results as one sweeps from left to right across the Gantt chart (in contrast, crossing tasks off a list can
indeed tell a person what has been completed, but it cannot show what has been done compared to what should have done at any given time.)
4. Interpreting Costs: One can make sense of what has been spent; if half of the budget has been spent, it should be noticeable whether or not half of the work has been completed (or
one should be able to tell why less than half of the budget has been spent even though the project has passed the half-way time mark, which can happen, for instance, if an especially expensive task
is coming up.) Or maybe the project is only 1/4 way along in terms of time duration, but 1/2 of the budget has already been spent - the project accountant may not detect the problem this since,
technically, there has not yet been overspend, but by way of this Gantt chart, it is clear spending is not going according to schedule. With these charts, potentinal problems like this can
more easily be monitored.
S = 8
S = 22
S = 22
S = 25